## Summary
Sprint | Date Range | Tasks | Bugs
Sprint 1: Core Foundation + AI Suggestions (Phase 1-3) | 2026-06-23 to 2026-06-29 | 4 | 0
Sprint 2: Keyword Research Feature | 2026-07-14 to 2026-07-18 | 10 | 3
Sprint 3: Scheduler, Deploy-to-WordPress, Backlinks, Security (overnight 24-task run) | 2026-07-19 to 2026-07-20 | 15 | 2
Sprint 4: On-Page Audit Generalization + AI Visibility | 2026-07-29 to 2026-08-07 | 4 | 0
Sprint 5: Deploy Infrastructure (Docker + CI/CD) | 2026-08-08 | 2 | 2
Sprint 6: Business Profile, Link Analyzer, WordPress Plugin, On-Page Polish | 2026-08-09 to 2026-08-17 | 9 | 2
Sprint 7: Deploy Verification + Stale-Task Reconciliation | 2026-08-28 to 2026-08-31 | 2 | 0
Sprint 8: On-Page Reliability Hardening | 2026-09-15 | 1 | 3
Sprint 9: Image Alt-Text + WordPress Plugin Rebuild (in progress, uncommitted) | 2026-09-17 to 2026-09-19 | 4 | 5
TOTAL

## Sprint Log
Sprint 1: Core Foundation + AI Suggestions (Phase 1-3) (2026-06-23 to 2026-06-29)
Tasks (4)
2026-06-23 | Initial project setup + scaffolding | Core | Done
2026-06-24 | DB schema and audit module | Core / Audit | Done
2026-06-25 | Phase 3: AI Suggestions engine + SQLite revert + Supabase stub | Suggestions | Done
2026-06-29 | Project detail UI enhancement, spider crawl animation, route redirects | UI | Done
Sprint 2: Keyword Research Feature (2026-07-14 to 2026-07-18)
Tasks (10)
2026-07-14 | Business Profile entity model + context-aware suggestions | Business Profile | Done
2026-07-14 | Added Keyword Research feature | Keyword Research | Done
2026-07-14 | Added /keywords/provider-status endpoint + live banner | Keyword Research | Done
2026-07-14 | Added unit tests for compute_trend and the keyword provider router | Keyword Research / Tests | Done
2026-07-14 | Detached Keyword Research into standalone workspaces | Keyword Research | Done
2026-07-14 | Keyword UX: bulk truncation notice, SERP modal, UTF-8 CSV export | Keyword Research | Done
2026-07-18 | Live provider health check; SERP + intent via Semrush | Keyword Research | Done
2026-07-18 | Worth-It scoring, Claude content briefs, full Keyword Research UX rework | Keyword Research | Done
2026-07-18 | Added worker-facing user guide for Keyword Research | Docs | Done
2026-07-18 | Rewrote roadmap as a 3-month sprint plan reconciled against actual code state | Planning | Done
Bugs (3)
2026-07-14 | Keyword lookups returned ambiguous results -- split into explicit ok / no_data / error states | Keyword Research | Fixed
2026-07-14 | Keyword lookups hardcoded to US market -- threaded real location through | Keyword Research | Fixed
2026-07-18 | Semrush CSV header parsing was broken | Keyword Research / Semrush | Fixed
Sprint 3: Scheduler, Deploy-to-WordPress, Backlinks, Security (overnight 24-task run) (2026-07-19 to 2026-07-20)
Tasks (15)
2026-07-19 | Task 2.1: added Job and Schedule tables | Scheduler | Done
2026-07-19 | Task 2.2: made Crawler Settings Save actually persist | Crawler | Done
2026-07-19 | Task 2.3: Job registry + crawl handler | Scheduler | Done
2026-07-19 | Tasks 2.4 + 2.5: APScheduler runner (subprocess-isolated jobs) + live Queue drawer | Scheduler | Done
2026-07-19 | Task 3.1: suggestion acceptance tracking (accept/reject/edit trail) | Suggestions | Done
2026-07-19 | Task 3.2: WordPress connection storage | WordPress | Done
2026-07-19 | Tasks 3.3 + 3.4: deploy suggestion to WordPress + rollback | WordPress / Deploy | Done
2026-07-19 | Task 3.5: expanded deployable fields (title, h1) | Deploy | Done
2026-07-19 | Task 4.1: rank-check job populates real SERP position | Rank Tracking | Done
2026-07-19 | Task 4.2: keyword refresh job + generic keyword-schedule endpoint | Scheduler | Done
2026-07-19 | Task 4.3: Easy Wins card uses real SERP position | Dashboard | Done
2026-07-19 | Task 5.1: Backlink models + live Semrush pull | Backlinks | Done
2026-07-19 | Task 5.2: backlink new/lost diffing job | Backlinks | Done
2026-07-19 | Task 5.3: auto-audit after crawl | Audit | Done
2026-07-19 | Task 6.3: basic security audit rules (SSL, security headers, robots.txt) | Security | Done
Bugs (2)
2026-07-19 | Keyword market not persisted per tracked keyword -- fixed US-default + location persistence | Keyword Research | Fixed
2026-07-20 | Job-lane scheduling conflict; nav fixes; public-repo presentation pass | Scheduler / UI | Fixed
Sprint 4: On-Page Audit Generalization + AI Visibility (2026-07-29 to 2026-08-07)
Tasks (4)
2026-07-29 | Wired up SEMrush on-page audit | On-Page SEMrush | Done
2026-07-30 | Added SEMrush API rationing support (unit budget protection) | On-Page SEMrush | Done
2026-08-07 | Generalized DataForSEO/SEMrush on-page audit to any project; crawler kill-switch; Security Testing tool; redesigned homepage | On-Page / Security | Done
2026-08-07 | Added AI Visibility tool: DataForSEO AI Overview citation + organic rank checks | AI Visibility | Done
Sprint 5: Deploy Infrastructure (Docker + CI/CD) (2026-08-08)
Tasks (2)
2026-08-08 | Added Docker setup for containerized deployment | Deploy Infra | Done
2026-08-08 | Added GitHub Actions deploy pipeline | Deploy Infra | Done
Bugs (2)
2026-08-08 | Deploy workflow heredoc broke inside nested SSM/JSON escaping | Deploy Infra | Fixed
2026-08-08 | Docker port mapping and DB bind-mount not idempotent | Deploy Infra | Fixed
Sprint 6: Business Profile, Link Analyzer, WordPress Plugin, On-Page Polish (2026-08-09 to 2026-08-17)
Tasks (9)
2026-08-09 | Added Gemini provider, dual-provider Backlinks, Competitor Analysis foundation | AI Providers / Backlinks | Done
2026-08-13 | Added Business Profile UI; wired Twitter/canonical/OpenGraph deploy; collapsed backlink lists; show current page values in issue tables | Business Profile / Deploy | Done
2026-08-14 | Added Link Analyzer tool | Link Analyzer | Done
2026-08-14 | Guarded Site Audit against duplicate/rapid re-runs with a configurable cooldown | On-Page SEMrush | Done
2026-08-16 | Shipped claude-wp-mcp WordPress plugin as an in-app download with setup guide | WordPress Plugin | Done
2026-08-17 | Raised site-scan page limits to 100 for crawler and DataForSEO on-page audit | Crawler / On-Page | Done
2026-08-17 | Added Link Analyzer health score, crawler kill-switch on running scheduler lane, redesigned links.html KPI cards | Link Analyzer | Done
2026-08-17 | Updated refresh-cost modal copy to match the 100-page crawl default | On-Page SEMrush | Done
2026-08-17 | Added decorative emoji to category labels, section headers, dashboard stats | UI Polish | Done
Bugs (2)
2026-08-14 | WordPress post-ID resolution failed for custom post types | WordPress | Fixed
2026-08-17 | On-page issue table only showed categories with hits, hiding clean categories | On-Page SEMrush | Fixed
Sprint 7: Deploy Verification + Stale-Task Reconciliation (2026-08-28 to 2026-08-31)
Tasks (2)
2026-08-28 | Added post-deploy verification via external DataForSEO re-fetch | Deploy Verification | Done
2026-08-31 | Added proactive stale on-page task reconciliation; remembered default max-crawl-pages per project | On-Page SEMrush | Done
Sprint 8: On-Page Reliability Hardening (2026-09-15)
Tasks (1)
2026-09-15 | Added per-image alt-text detail, issue history stability, manual suggestions, CSV export | On-Page SEMrush / Suggestions | Done
Bugs (3)
2026-09-15 | On-page audit spinner never stopped on errored tasks | On-Page SEMrush | Fixed
2026-09-15 | Infinite auto-refresh loops replaced with one-shot checks + stale-job cleanup | On-Page SEMrush | Fixed
2026-09-15 | Deploy pipeline unreliable -- auto-run migrations, prevent disk exhaustion, fail loudly | Deploy Infra | Fixed
Sprint 9: Image Alt-Text + WordPress Plugin Rebuild (in progress, uncommitted) (2026-09-17 to 2026-09-19)
Tasks (4)
2026-09-17 | Per-image alt-text: direct-site image parsing spike, WP media_id detection, MCP plugin backlog scoping | Image Alt / WordPress | Done (uncommitted)
2026-09-18 | Built vtechseo-agent, new lean WordPress plugin (23 tools) replacing claude-wp-mcp (67 tools) | WordPress Plugin | Done (uncommitted)
2026-09-19 | Added per-image 'Fix Now' UI: write-your-own or AI-generate alt text scoped to one image, not the whole page | Image Alt / Suggestions | Done (uncommitted)
2026-09-19 | Added suggestions.image_src column (migration 027) + scoped generation/prompt/storage per image | Image Alt / Suggestions | Done (uncommitted)
Bugs (5)
2026-09-18 | wordpress.py still hardcoded to old plugin REST namespace (cwpm/v1) after new plugin registered under vtseo/v1 -- would have broken both live site connections | WordPress | Fixed (uncommitted)
2026-09-18 | Test-connection stalled up to 5 minutes -- _resolve_all_pages ran synchronously inline; moved to BackgroundTasks with its own DB session | WordPress | Fixed (uncommitted)
2026-09-18 | Concurrent test-connection clicks could stack duplicate crawl sweeps + racing SQLite writes -- added in-flight guard | WordPress | Fixed (uncommitted)
2026-09-18 | Frontend fetch() for test-connection had no timeout -- could hang forever; added 25s AbortController timeout | WordPress / Frontend | Fixed (uncommitted)
2026-09-19 | Fix-modal image list scroll position reset to top on every re-render -- fixed scroll save/restore | Image Alt / UI | Fixed (uncommitted)